## Hybrid Project Kottur STU
CHECK LIST OF THE PROJECT STATUS
Hybrid Kottur- 600MW- Virudhunagar - Tamil Nadu
Section | Checklist Item | Status | Remarks | Supporting Doc if any | Target Closure Date
Project Overview | SPV Incorporated?
| Project Capacity Finalized (MW) | 600MW
| For solar AC and DC capacity required | 200MW/260MWp
| Wind Capacity | 400MW
Land | Total Land Identified | yes
| Type of land - Private/Revenue | Private
| Land Under Possession (%) | 20% | In the name of Developer
| 30-Year Title Search Completed | Under progress
| NA Conversion Completed | TBC
| Leased / to be leased / outright purchase | Outright purchase
Site co-ordinates / outer boundary
Solar Land | Acres | 280Acres | In the name of Developer
Wind Land | How many locations and acres per location | Identified/ 10Acres
Pooling Station Land | Acres | Identified
Approach Road Land | Approach Road Land status | Route Survey Done
Resource & Yield | Wind Data (12–24 Months) Available | NIWE data
| Annual Average Wind Speed m/s at mast height | 6.35m/s
| Wind Mast Height | 100m
| Near by operating wind farm, how many km away? | 5KM
| Solar Resource Information if any | GHI- 1961.5kwh/m2
| Nearby solar project if any? | Yes
Grid Connectivity | STU/CTU Feasibility Approval Obtained | Under progress
| Bay Allocation Confirmed | Under progress
| Grid Connectivity Permission and its validity | Under progress
| GSS Name, Voltage ratio, Transformer capacity | Virudhunagar 765/400Kv 2*1500Mva
| Pooling Station Details if any | To be constructed
| Line Disctance from GSS to Site / Pooling Station in km | 46KM for Wind/ 12KM for Solar
| Any other option/s for grid connectivity? | NO
Regulatory Approvals | State Nodal Approval and its validity | To be Applied
| Environmental Clearance (if applicable) | To be Applied
| Aviation / Forest Clearance status | To be Applied
| Any other govt. permit | To be Applied
PPA | PPA status
Commercial proposal with terms and conditions. Pl mention the inclusions, GST etc |  | Pl attached separate sheet if required

## Solar Project PGCIL CTU
CHECK LIST OF THE PROJECT STATUS
150MW- Vadakuvanthanam- Tamil Nadu
Section | Checklist Item | Status | Remarks | Supporting Doc if any | Target Closure Date
Project Overview | SPV Incorporated?
| Project Capacity Finalized (MW) | 150MW
| For solar AC and DC capacity required | 150MW/195MWp
Wind Capacity
Land | Total Land Identified | yes
| Type of land - Private/Revenue | Private
| Land Under Possession (%) | 40% | In the name of Developer
| 30-Year Title Search Completed | Under progress
| NA Conversion Completed | TBC
| Leased / to be leased / outright purchase | outright purchase
Site co-ordinates / outer boundary
Solar Land | Acres | 200Acres | In the name of Developer
Wind Land | How many locations and acres per location
Pooling Station Land | Acres | To be Constructed
Approach Road Land | Approach Road Land status | Route Survey Done
Resource & Yield | Wind Data (12–24 Months) Available
Annual Average Wind Speed m/s at mast height
Wind Mast Height
Near by operating wind farm, how many km away?
| Solar Resource Information if any | GHI- 1973.5kwh/m2
| Nearby solar project if any? | Yes
Grid Connectivity | STU/CTU Feasibility Approval Obtained | Obtained
| Bay Allocation Confirmed | Obtained
| Grid Connectivity Permission and its validity | Exsisting
| GSS Name, Voltage ratio, Transformer capacity | Vadakuvanthanam 400/230Kv 6*500MVa
| Pooling Station Details if any | To be Constructed
| Line Disctance from GSS to Site / Pooling Station in km | 15KM
| Any other option/s for grid connectivity? | NO
Regulatory Approvals | State Nodal Approval and its validity | To be Applied
| Environmental Clearance (if applicable) | To be Applied
| Aviation / Forest Clearance status | To be Applied
| Any other govt. permit | To be Applied
PPA | PPA status
Commercial proposal with terms and conditions. Pl mention the inclusions, GST etc |  | Pl attached separate sheet if required

## Solar Project Murukeri STU
CHECK LIST OF THE PROJECT STATUS
Murukeri- 50MW- Villupuram- Tamil Nadu
Section | Checklist Item | Status | Remarks | Supporting Doc if any | Target Closure Date
Project Overview | SPV Incorporated?
| Project Capacity Finalized (MW) | 50MW
| For solar AC and DC capacity required | 50MW/65MWp
| Wind Capacity | -
Land | Total Land Identified | yes
| Type of land - Private/Revenue | Private
| Land Under Possession (%) | 50% | In the name of Developer
| 30-Year Title Search Completed | Under progress
| NA Conversion Completed | TBC
| Leased / to be leased / outright purchase | outright purchase
Site co-ordinates / outer boundary
Solar Land | Acres | 100Acres | In the name of Developer
Wind Land | How many locations and acres per location | -
Pooling Station Land | Acres | To be Constructed
Approach Road Land | Approach Road Land status | Route Survey Done
Resource & Yield | Wind Data (12–24 Months) Available
Annual Average Wind Speed m/s at mast height
Wind Mast Height
Near by operating wind farm, how many km away?
| Solar Resource Information if any | GHI- 1994.4kwh/m2
| Nearby solar project if any? | NA
Grid Connectivity | STU/CTU Feasibility Approval Obtained | Obtained
| Bay Allocation Confirmed | Confirmed
| Grid Connectivity Permission and its validity | Under progress
| GSS Name, Voltage ratio, Transformer capacity | Murekeri 110/33kv 2*16MVa
| Pooling Station Details if any | Murukeri
| Line Disctance from GSS to Site / Pooling Station in km | 15KM/ 5KM
| Any other option/s for grid connectivity? | NO
Regulatory Approvals | State Nodal Approval and its validity | To be Applied
| Environmental Clearance (if applicable) | To be Applied
| Aviation / Forest Clearance status | To be Applied
| Any other govt. permit | To be Applied
PPA | PPA status
Commercial proposal with terms and conditions. Pl mention the inclusions, GST etc |  | Pl attached separate sheet if required

## Hybrid Project OTP STU
CHECK LIST OF THE PROJECT STATUS
Otapidaram- 100MW- OTP - Tamil Nadu
Section | Checklist Item | Status | Remarks | Supporting Doc if any | Target Closure Date
Project Overview | SPV Incorporated?
| Project Capacity Finalized (MW) | 100MW
| For solar AC and DC capacity required | 75MW/100MWp
| Wind Capacity | 25MW
Land | Total Land Identified | yes
| Type of land - Private/Revenue | Private
| Land Under Possession (%) | Under progress
| 30-Year Title Search Completed | Under progress
| NA Conversion Completed | TBC
| Leased / to be leased / outright purchase | outright purchase
Site co-ordinates / outer boundary
Solar Land | Acres | 50Acres
Wind Land | How many locations and acres per location
Pooling Station Land | Acres | To be constructed
Approach Road Land | Approach Road Land status | Route Survey Done
Resource & Yield | Wind Data (12–24 Months) Available
Annual Average Wind Speed m/s at mast height
Wind Mast Height
Near by operating wind farm, how many km away?
| Solar Resource Information if any | GHI- 1991kwh/m2
| Nearby solar project if any? | Yes
Grid Connectivity | STU/CTU Feasibility Approval Obtained | Yes
| Bay Allocation Confirmed | Yes
| Grid Connectivity Permission and its validity | Under progress
| GSS Name, Voltage ratio, Transformer capacity | Otapidaram 400/230 2*500MVa
| Pooling Station Details if any | To be constructed
| Line Disctance from GSS to Site / Pooling Station in km | 18KM
| Any other option/s for grid connectivity? | NO
Regulatory Approvals | State Nodal Approval and its validity | To be Applied
| Environmental Clearance (if applicable) | To be Applied
| Aviation / Forest Clearance status | To be Applied
| Any other govt. permit | To be Applied
PPA | PPA status
Commercial proposal with terms and conditions. Pl mention the inclusions, GST etc |  | Pl attached separate sheet if required